## Sheet 1 - Bug List - Minimal -
Bug & Task List - Minimal
Bug Number | Description | Priority | Notes | Status | Owner
1 | Repeatedly jumping while stationary will move the player ever so slightly. | C | None | Fixing
2 | Game looks compressed/stretched on aspect ratios that aren’t 16/9 due to current resolution lock. | A | Due to our own code locking us to this aspect ratio to solve UI issues. Investigate better methods. | Fixing
3 | If the player jumps while touching two objects (e.g floor & platform) then they cannot jump again. | A | None | Fixing
4 | Player can constantly jump on the underside of platforms. | B | Temporarily fixed by having multiple objects combined to make up the platform. Not ideal. | Temp Fixed
5 | The player can jump in the air after sliding off the side of a platform. | B | None | Fixing
6 | Saved’ text appears after loading into the game. | C | None | Fixing
7 | Finish writing the game design document. | A | None | TODO | Callum
8 | Play the current version of the game to get up to speed on where we left off. | A | Get to grips with the work that we already have in place. Go over the existing features and code, make any changes required to improve the gameplay/performance. | TODO | Callum & Taco
9 | Create save file when loading into game. | A | Check if the user has a save file when we first boot the game, if not then create one. We should also make this file hidden if possible | TODO